## Sheet1
Name | Josh Doyle | Aber User ID | jod32 | Week Starting | 2015-12-07 | Total hours accounted this week: 06:00 |  | 6:00
Task ID | Friendly Task Name | Task Description | Task Type | Date Completed | Time Taken | Time Budgeted | Comments
SE_05_TCLI_03 | Implement Classes from design specification and adhering to interfaces | Implemented Classes that handled Tasks (i.e. loading and displaying) as well as some GUI Classes for the first prototype demonstration | Code | 2015-12-09 | 4:00 | 2:00 | There were some difficulties with displaying a table correctly due to my lack of experience in building GUI interfaces with Swing
SE_05_TCLI_06 | Performance and bug fixing | Fixed bugs relating to Tasks not displaying when the user tried to edit | Code | 2015-12-10 | 2:00 | 0:30 | This was not as trivial as anticipated. The error was spotted with the help of David Fairbrother.