## Sheet1
Name | John Smith | Aber User ID | abc123 | Week Starting | 0 | Total hours accounted this week: 06:00 |  | 6:00
Task ID | Friendly Task Name | Task Description | Task Type | Date Completed | Time Taken | Time Budgeted | Comments
SE_05_DEGN_04 | Design and Create Mock-up of User Interface | Created UI designs for all TaskerCLI windows | Design | 2015-11-20 | 6:00 | 3:00 | This took longer than I expected it to due to doing this task using Micrsoft Office. This created difficulties in creating a representative design that took a long time to work around.