## Sheet1
Name | Oliver Earl | Aber User ID | ole4 | Week Starting | 2015-10-26 | Total hours accounted this week: 05:45 |  | 5:45
Task ID | Friendly Task Name | Task Description | Task Type | Date Completed | Time Taken |  | Comments
SE_05_DEGN_01 | Create systems applications documentation | Updated PHP/TaskerMan research with more information | Documentation | 2015-10-28 | 0:15 |  | Added screenshots that would later go on to be used in the main deliverable
SE_05_DEGN_02 | Create application interaction documentation which lists to format data will be transmitted in | More research onto PHP/TaskerMan and DB integration, requirements | Documentation | 2015-10-28 | 0:30 |  | Further research was added
SE_05_DEL_01 | Interaction and high level design deliverable | Compiling all previous tasks and information into final deliverable document, adding citations and relevant information, formatting screenshots and images | Documentation | 2015-10-29 | 5:00 |  | Most of the work was done although some was contributed by daf5. Took quite a long time due to the tediousness of the task at hand and the nature of combining documents. In future we are probably going to come up with a more reliable solution for document collaborations, such as the use of Google Docs' collaboration tool