## Sheet1
Name | Josh Doyle | Aber User ID | jod32 | Week Starting | 2016-01-25 | Total hours accounted this week: 21:00 |  | 45:00
Task ID | Friendly Task Name | Task Description | Task Type | Date Completed | Time Taken | Time Budgeted | Comments
SE_05_TCLI_04 | Implement Task Synchronisation Logic | Worked on loading & saving of Tasks, and preparing Tasks for synchronising to the database | Code | 2016-01-27 | 0.20833 | 1:00 | Development of this was seriously delayed by some unusual behaviour by Java that was tricky to pin down. Calling toString on a char array did not return a String of the char array but a String of the pointer to the char array.
SE_05_TCLI_06 | Performance and bug fixing | Fixing bugs that arose during development, as well as fixing regressions | Code | 2016-01-29 | 1899-12-31 01:00 | 10:00 | Several problems were much harder to spot and/or fix than anticipated. Testing and fixing continued until the final day, making this a week-long task.
SE_05_TCLI_05 | Implement GUI | Some changes to GUI that were overlooked. Added log out button, implemented changing of conenction settings labels, fixed issues with windows not closing correctly, added saving of data entered by the user, added live updating of Task display. | Code | 2016-01-28 | 0.625 | 10:00 | Some aspects could not be implemented in the way I expected which created a few hours of delays.