## Sheet1
Name | Oliver Earl | Aber User ID | ole4 | Week Starting | 2016-01-25 | Total hours accounted this week: 11:00 |  | 35:00
Task ID | Friendly Task Name | Task Description | Task Type | Date Completed | Time Taken |  | Comments
SE_05_TMAN_03 | Basic editing of tasks | Adding adding/remove/edit tasks | Development | 2016-01-25 | 10:00 | 15:00 | Went okay but extra time was spent debugging and ensuring that the software behaved correctly across the modal windows
SE_05_TMAN_02 | HTML/CSS Editing | Ongoing adding of static HTML/CSS | Development | 2016-01-28 | 5:00 | 10:00 | Ongoing adding of necessary HTML/CSS - mostly offloaded to tma1 but my input was required occasionally
SE_05_TMAN_03 | Basic editing of users | Adding adding/remove/edit users | Development | 2016-01-29 | 2:00 | 5:00 | This was much easier to implement as there wasn't any annoying task elements to implement
SE_05_TMAN_05 | JavaScript validation | Adding JavaScript validation | Development | 2016-01-29 | 3:00 | 5:00 | Huge pain to have to constantly test that the validation is effective but it appears to work
SE_05_TMAN_06 | TaskerMAN Bug Fixing | Bug Fixing | Development | 2016-01-29 | 15:00 | 10:00 | Took longer than expected due to extensive testing bringing up several edge cases