## Sheet1
Name | David Fairbrother | Aber User ID | daf5 | Week Starting | 2015-11-09 | Total hours accounted this week: 02:15 |  | 2:15
Task ID | Friendly Task Name | Task Description | Task Type | Date Completed | Time Taken | Time Budgeted | Comments
SE_05_DEL_02 | Complete Test specification deliverable | First QA check | Documentation | 2015-11-11 | 1:00 | 1:00 | Meeting with QA about test specification several enchaments and minor tweaks suggested.
SE_05_DEL_02 | Complete Test specification deliverable | Package and submit test specification for QA process then submit to Blackboard | Documentation | 2015-11-13 | 1:15 | 2:00 | The revised test specification was quickly put through QA due to the minor amount of changes significantly reducing the task time