## Sheet1
Name | David Fairbrother | Aber User ID | daf5 | Week Starting | 2015-12-07 | Total hours accounted this week: 03:40 |  | 3:40
Task ID | Friendly Task Name | Task Description | Task Type | Date Completed | Time Taken | Time Budgeted | Comments
SE_05_TCLI_04 | Implement task synchronisation logic | Create and test connection to database | Code | 2015-12-09 | 3:00 | 1:30 | JDBC had several caveats and complications in its usage the prototyping did not pickup leading to a large additional delay
SE_05_TCLI_06 | Performance and bug fixing | Fixing null pointer bug in GUI | Debug | 2015-12-09 | 0:10 | 1:00 | What was initially thought as a complex bug was the compiler getting slightly confused, switching 2 lines fixed the issue
SE_05_TSRV_01/02 | Create schema and index | Manually created databased structure for first prototype | Code | 2015-12-10 | 0:30 | 0:00 | Originally a script was going to create the DB however the design did not allow the requirements for task elements to work. The database was manually created and tweaked using MYSQL workbench