## Sheet1
Name | David Fairbrother | Aber User ID | daf5 | Week Starting | 2015-01-25 | Total hours accounted this week: 00:00 |  | 24:00
Task ID | Friendly Task Name | Task Description | Task Type | Date Completed | Time Taken | Time Budgeted | Comments
SE_05_TCLI_04 | Implement remaining sync logic | Add more methods to process SQL data to Java objects. Complete writing back to database | Code | 2015-11-27 | 5:00 | 4:00 | Misunderstanding of the fact a resultset is read only meant some refactoring impacted time
SE_05_TCLI_05 | Implement GUI | Combining the database classes and GUI classes into a single package | Code | 2015-11-28 | 1:30 | 3:00 | The database and GUI connected and worked first time catching us by surprise.
SE_05_TCLI_06 | Bug fixing | TaskerCLI bug fixing | Code/Testing | 2015-11-29 | 15:00 | 5:00 | It rapidly became apparent the design for TaskerCLI was unsuitable, due to the fact nobody had experience of completing this type of program the way the code was intended to work and how it actually worked caused many issues. This was compounded by the nature of the program. To meet performance requirements threading was used. This lead to bugs such as race conditions or the main window randomly closing. This significantly delayed TaskerCLI from its Wednesday finish to a Friday finish
SE_05_TCLI_03/04/05 | TaskerSRV implement test data and tweaks | TaserSRV bug fixing/changes | Code | 2015-11-29 | 2:00 | 4:00 | Using the previously exported test data in a CSV a script was written to wrap the test data in SQL for a script. This meant the final script which populates the database was created in a significantly shorter time. The database was also changed as there was some minor bugs such as a Date being mistyped as VARCHAR.
SE_05_PM_04 | Delviery of software | Package and deliver software | Project Management | 2015-11-29 | 0:30 | 1:00 | Due to a looming deadline this task was completed as fast as possible meaning it only took 30 minutes.