## Sheet1
Name | Jonathan Englund | Aber User ID | jee17 | Week Starting | 2016-01-25 | Total hours accounted this week: 18:00 |  | 18:00
Task ID | Friendly Task Name | Task Description | Task Type | Date Completed | Time Taken | Time Budgeted | Comments
| Implemted Email validation on TaskerCli | The emails are checked when entered into databse but need to be checked that they are in fact valid emails | Code | 2016-01-25 | 2:00 | 1:00 | This took longer than expected as there was some cnfusion on what data we would allow and what was be considered invalid
| TaskerMan switch | Was switched to TaskerMan so had to catch up with everything that had been changed | Code | 2016-01-26 | 3:00 | 4:00 | I spent the mjority of the day looking over the code and being brought up to speed with what needed doing
| TaskerMan Update | Noticed a few things were missing from TaskeMan comapared to req spec and created issues for those most notably task elements | Code | 2016-01-26 | 2:00 | 2:00 | Some major components were still missing and so I wanted to make sure that these were adressed asap
| taskAdd Update | task Add had not been implemented with the db connection | Code | 2016-01-27 | 4:00 | 4:00 | Added the PDO prepared statements for taskAdd which took a while and some conversions needed to happen as status was stored on db as int and as a string in the form
| addEntry | addEntry.php was created to handle Posted values to be sent to db | Code | 2016-01-27 | 4:00 | 4:00 | because taskAdd was included we needed an extra place to hold the data
| added JavaDoc | JavaDoc added for all TakerCli methods | Code | 2016-01-29 | 3:00 | 3:00 | added Javadoc to all remaining mehtods that Josh had missed excluding the Junit methods