## Sheet1
Name | Oliver Earl | Aber User ID | ole4 | Week Starting | 2016-02-08 | Total hours accounted this week: 01:00 |  | 25:00
Task ID | Friendly Task Name | Task Description | Task Type | Date Completed | Time Taken |  | Comments
SE_05_MAINT _01 | TaskerMAN Maintenance manual | Writing the TaskerMAN Maintenance manual | Documentation | 2016-02-10 | 5:00 | 10:00 | No problems completing this apart from the tedium required
SE_05_QA_01/02/03/04 | Documentation QA | Final QA for document handover | Documentation | 2016-02-15 | 10:00 | 10:00 | Extensive QA of all documents, including testing and document specification.
SE_05_QA_01/02/03/05 | Updating Design Spec | Updating design spec to closer match current system | Documentation | 2016-02-15 | 10:00 | 10:00 | Extensive modification of design spec. This includes the drawing of new diagrams, editing of existing ones, new UI sketches and various additions to improve our design overall.